## 📋 Cover
👥 ICS Migration RACI & Skills Framework Migrating the Unmigrateable — Study Notes ¦ [MtU #09]
Phase — People & Governance ¦ Who Does What, Who Decides, Who Needs to Know
PROJECT INFORMATION
Facility / Site Name
Project Lead
OT Lead
IT Security Lead
| Safety Engineer | N/A if no SIL systems in scope
Plant Manager
Programme Start Date
| Document Version | v1.0
RACI KEY
| R — Responsible | Does the work. Executes the task. Can be multiple people per activity.
| A — Accountable | Owns the outcome. Signs off. Only ONE person per activity — the buck stops here.
| C — Consulted | Input required before the activity is complete. Two-way communication.
| I — Informed | Kept up to date. Does not need to provide input. One-way communication.
| R/A | One person is both responsible and accountable. Common for specialist activities.
SHEETS IN THIS WORKBOOK
| 👥 RACI Matrix | Who does what across all six phases. Agreed before project starts.
| 🧑‍💼 Role Definitions | What each role needs to know, do and decide. Skills requirements per role.
| 🎓 Skills Gap Assessment | Where each team member is today vs. where they need to be.
| 📚 Training Pathways | Qualifications, courses and self-study routes for each role.
| 📖 Reference | The three tribes, RACI principles and OT security career pathways.
⚡ Migrating the Unmigrateable — Study Notes ¦ [MtU #09] ¦ Free resource — cite with attribution

## 👥 RACI Matrix
👥 RACI Matrix ¦ ICS Migration Programme ¦ Agree Before Project Starts ¦ [MtU #09]
← Activity |  | OT Lead / Process Expert | IT Security Lead | Project / Compliance Lead | Safety Engineer | Plant Manager | Operations Supervisor | Vendor / Contractor | IT Manager | Board / Senior Mgmt
ID | Phase / Activity | Role 1 | Role 2 | Role 3 | Role 4 | Role 5 | Role 6 | Role 7 | Role 8 | Role 9
P0-01 | PHASE 0 — ASSET DISCOVERY
P0-02 | Initiate project — scope, objectives, stakeholder alignment | C | C | R/A | C | A | I |  | I | I
P0-03 | Passive network monitoring deployment and configuration | C | R | I |  | I | I | C | R
P0-04 | Physical walkdown — asset identification | R | C | I | C | I | I | C
P0-05 | Documentation review — existing diagrams, maintenance records | Role 1: R; Role 2: C; Role 3: R; Role 5: I; Role 6: I
P0-06 | Asset inventory compilation and sign-off | R | C | R/A |  | A | I |  | I
P0-07 | Network topology mapping | Role 1: C; Role 2: R; Role 3: R; Role 5: I; Role 8: I
P0-08 | Initial risk flags — EOL, CVE, undocumented access | Role 1: C; Role 2: R; Role 3: R; Role 4: C; Role 5: I
P1-01 | PHASE 1 — RISK ASSESSMENT
P1-02 | Risk scoring — vulnerability dimension | Role 1: R; Role 2: R; Role 3: C; Role 5: I
P1-03 | Risk scoring — consequence dimension | R | C | C | C | I | C
P1-04 | Risk scoring — exposure dimension | Role 1: C; Role 2: R; Role 3: C; Role 5: I
P1-05 | Zone map and conduit identification | R | R | C | C | I | I
P1-06 | Priority shortlist compilation | C | C | R/A |  | A | I |  |  | I
P1-07 | Risk assessment sign-off — plant management | C | C | R | C | A | I |  |  | I
P2-01 | PHASE 2 — SEGMENTATION & ISOLATION
P2-02 | Segmentation design — zone architecture, VLAN plan | R | R | C | C | I | I |  | I
P2-03 | Firewall rule design and approval | C | R | C | C | A | I |  | A
P2-04 | Change request — MOC process initiation | R | C | R | C | A | I |  | I
P2-05 | VLAN implementation and verification | C | R | I |  | I | I | C | R
P2-06 | Remote access hardening — MFA, session logging, IP restriction | C | R | C |  | I | I | C | R
P2-07 | Decommission undocumented access paths | R | R | C |  | A | I | C | I
P2-08 | Compensating controls — EOL device documentation and sign-off | R | C | R/A | C | A | I
P2-09 | Segmentation verification and sign-off | R | R | C | C | A | C |  | I
P3-01 | PHASE 3 — CONTROLLED MIGRATION
P3-02 | Migration approach selection per device | R | C | C | C | A | I | C
P3-03 | Staging environment build and configuration | Role 1: R; Role 2: C; Role 3: I; Role 5: I; Role 7: C
P3-04 | Staging test execution — all 12 test categories | R | R | C | C | I | C | C
P3-05 | Pre-migration checklist completion and sign-off | R | C | R | C | A | C
P3-06 | Operator training on new system | Role 1: C; Role 3: R; Role 5: I; Role 6: R/A; Role 7: C
P3-07 | Change window — cutover execution | R | R | C | C | I | R | C | I
P3-08 | Go/No-Go gate decision | bar: Role 1 to Role 9
P3-09 | Rollback — if triggered | R | R | C | C | A | R | C | I
P3-10 | Post-migration 24h and 1-week review | R | C | R/A | C | A | R
P4-01 | PHASE 4 — VALIDATE & DOCUMENT
P4-02 | Validation test execution — functional, security, performance, integration | R | R | C | C | I | C
P4-03 | Validation test report compilation and sign-off | C | C | R/A | C | A | I
P4-04 | Compliance evidence summary — per asset | R: C; C: R/A; A: I | I
P4-05 | Asset register update — decommission old, activate new | R | C | R |  | I |  |  | I
P4-06 | Lessons learned record | R | R | R/A | C | I | C
P5-01 | PHASE 5 — OPERATE & MONITOR
P5-02 | Monthly CVE checks and vulnerability log update | C | R | C |  | I |  |  | I
P5-03 | ICS-CERT advisory review and response | R | R | C | C | I |  |  | I
P5-04 | Monitoring alert investigation and closure | R | R | C | C | I | C |  | I
P5-05 | Quarterly access control review | C | R | R |  | A | I |  | A
P5-06 | Quarterly risk register review | R | C | R/A | C | A | I |  |  | I
P5-07 | Quarterly OT security review meeting | C | C | R | C | A | I |  | I | I
P5-08 | Annual compliance evidence pack refresh | C | C | R/A | C | A | I |  | I | I
P5-09 | Annual full vulnerability assessment | R | R | C | C | I |  |  | I
P5-10 | NIS2 incident reporting — if triggered | R | R | R | C | A | I |  | I | A
G-01 | GOVERNANCE
G-02 | OT security programme ownership | C: R/A; A: A | I
G-03 | Budget approval — programme investment | [8 empty] | A | bar: C; A
G-04 | Board / management reporting — quarterly | [8 empty] | A | bar: R to I
G-05 | Vendor management — security requirements in contracts | C | C | R |  | A |  | C | C
G-06 | New staff — OT security briefing | R | C | R |  | I | I |  | I

## 🧑‍💼 Role Definitions
🧑‍💼 Role Definitions ¦ What Each Role Needs to Know, Do & Decide ¦ [MtU #09]
OT Lead / Process Expert
| Primary responsibility | Understand the physical process and control systems. Bridge between technical team and plant operations.
| Must know | Process dependencies, control logic, vendor relationships, communication timing requirements, SIL implications, what each device does in operational context.
| Must be able to do | Explain any device's role in the process. Identify undocumented dependencies. Flag process impacts before changes are made. Operate as process authority during change windows.
| Must be able to decide | Whether a proposed change is safe to make on a live process. When to pause a migration for process safety reasons.
| Ideal background | Senior OT/controls engineer with 7+ years on the specific site or similar facility. Must be genuinely invested — not assigned as a box-ticking exercise.
| Key risk if wrong person | Project proceeds without process understanding. Migration breaks something nobody knew was dependent. Veteran engineer's knowledge is lost.
IT Security Lead
| Primary responsibility | Network architecture, security tooling, compliance framework, firewall and segmentation design.
| Must know | OT protocol fundamentals (Modbus, DNP3, EtherNet/IP, PROFIBUS). Passive monitoring tools. IEC 62443 zone and conduit model. Why active scanning is dangerous in OT.
| Must be able to do | Design VLAN segmentation without breaking OT communication. Configure OT-aware firewall rules. Interpret monitoring tool alerts in OT context. Conduct CVE assessments on OT assets.
| Must be able to decide | Security architecture decisions. Firewall rule approval. Remote access policy. Monitoring tool configuration.
| Ideal background | IT security professional with OT exposure — GICSP qualified or working toward it. Has spent time on an OT site. Understands the difference between IT and OT risk models.
| Key risk if wrong person | IT security principles applied to OT without adaptation. Active scanning crashes PLCs. Firewall rules break control loops. Security tool disrupts timing-sensitive communications.
Project / Compliance Lead
| Primary responsibility | Programme methodology, documentation, compliance evidence, stakeholder management, business case.
| Must know | IEC 62443 framework. NIS2 Article 21 obligations. Project management fundamentals. How to translate technical findings into business language. The MtU series templates inside-out.
| Must be able to do | Maintain project plan across all phases. Produce the documentation set that satisfies auditors. Facilitate IT/OT collaboration when stuck. Write a business case that gets approved. Run the RACI process.
| Must be able to decide | Project timeline and phase boundaries. When to escalate to plant management. What goes in the compliance evidence pack.
| Ideal background | Consultant or project manager with OT security experience. IT/security background transitioning into OT — exactly the profile this series is building. IEC 62443-2-1 training helpful.
| Key risk if wrong person | Methodology without operational context. Documentation that doesn't reflect reality. Business case that doesn't speak to the board. OT and IT teams working in parallel without coordination.
Safety Engineer
| Primary responsibility | Safety impact assessment for any change near SIL-rated equipment or safety instrumented systems.
| Must know | IEC 61508 / IEC 61511. SIL assessment methodology. Management of Change for safety-critical systems. The facility's safety case.
| Must be able to do | Assess whether a proposed migration or segmentation change affects any safety function. Run the MOC process for SIL systems. Sign off on SIL-adjacent changes.
| Must be able to decide | Whether any change is safe to make on SIL-rated equipment. When a change requires a full safety case update.
| Ideal background | Functional safety engineer with IEC 61511 competency. Facility-specific safety case knowledge essential.
| Key risk if wrong person | SIL system affected by change without proper assessment. Safety function impaired. This is not a project risk — it is a safety risk with potential for serious harm.
Plant Manager
| Primary responsibility | Accountable for programme outcomes. Budget authority. Final sign-off on major decisions and change windows.
| Must know | Business risk exposure. Programme status at each phase. What the board needs to hear.
| Must be able to do | Make Go/No-Go decisions. Approve budget. Communicate programme status upward. Remove organisational blockers.
| Must be able to decide | Programme investment approval. Change window authorisation. Escalation to board.
| Ideal background | Operational leadership with P&L accountability. Does not need technical depth — needs trust in the technical team and authority to act on their recommendations.
| Key risk if wrong person | Decisions delayed waiting for approval. Budget not released. Programme stalls. Or conversely — programme pushed forward without appropriate oversight.

## 🎓 Skills Gap Assessment
🎓 Skills Gap Assessment ¦ Where We Are vs. Where We Need to Be ¦ [MtU #09]
Skill Area | Required Level (1–4) | OT Lead Current | OT Lead Gap | IT Security Current | IT Security Gap | Project Lead Current | Project Lead Gap | Safety Eng Current | Safety Eng Gap | Training Action | Priority
Skill levels: 1 = Awareness only ¦ 2 = Working knowledge ¦ 3 = Practitioner ¦ 4 = Expert / can train others. Gap = Required – Current (positive = gap, negative = exceeds requirement)
OT/ICS Protocol Knowledge (Modbus, DNP3, EtherNet/IP, PROFIBUS) | 3 | 4 | -1 | 2 | 1 | 2 | 1 | 1 | 2 | IT Sec: GICSP study. Project Lead: IEC 62443 training includes protocol overview. | 🟡 Medium
PLC/DCS/SCADA Operations — how control systems work in practice | 3 | 4 | -1 | 1 | 2 | 1 | 2 | 1 | 2 | IT Sec + Project Lead: site visits, vendor training days, ICS simulation labs. | 🟠 High
Process Safety — SIL, functional safety, IEC 61508/61511 | 3 | 3 | 0 | 1 | 2 | 1 | 2 | 4 | -1 | IT Sec + Project Lead: IEC 61511 awareness training. Rely on Safety Engineer for decisions. | 🟡 Medium
OT Vendor Ecosystem — Siemens, Rockwell, Schneider, Honeywell | 2 | 4 | -1 | 1 | 1 | 2 | 0 | 1 | 1 | All: vendor training days, TIA Portal / Studio 5000 introductory courses. | 🟢 Low
Network Architecture — VLANs, firewalls, DMZ design | 3 | 1 | 2 | 4 | -1 | 2 | 1 | 1 | 2 | OT Lead: networking fundamentals course. CompTIA Network+ as foundation. | 🟠 High
OT-Aware Security Tools — Nozomi, Claroty, Dragos | 3 | 1 | 2 | 3 | 0 | 2 | 1 | 1 | 2 | OT Lead: vendor training. Project Lead: tool overview training. | 🟡 Medium
Vulnerability Management — CVE database, CVSS, OT-specific CVEs | 3 | 1 | 2 | 4 | -1 | 3 | 0 | 1 | 2 | OT Lead: CISA ICS-CERT advisory subscription + self-study. | 🟡 Medium
Incident Response — OT-specific scenarios and playbooks | 3 | 2 | 1 | 3 | 0 | 2 | 1 | 1 | 2 | All: OT IR tabletop exercise. SANS ICS curriculum. | 🟠 High
IEC 62443 — zone model, security levels, management system | 3 | 1 | 2 | 2 | 1 | 3 | 0 | 1 | 2 | OT Lead + IT Sec: ISA/IEC 62443 Cybersecurity Certificate Program. | 🟠 High
NIS2 — Article 21 obligations, incident reporting, penalties | 2 | 1 | 1 | 2 | 0 | 3 | -1 | 1 | 1 | OT Lead: NIS2 awareness briefing. Project Lead already at practitioner level. | 🟢 Low
Risk Assessment — consequence-based OT methodology | 3 | 2 | 1 | 2 | 1 | 3 | 0 | 2 | 1 | All: MtU #02 Risk Scoring Matrix methodology walkthrough. | 🟡 Medium
Change Management — OT MOC process | 3 | 3 | 0 | 2 | 1 | 2 | 1 | 2 | 1 | IT Sec + Project Lead: review OT MOC process with OT Lead. MtU #04 methodology. | 🟢 Low
Business Case — translating OT risk to financial language | 2 | 1 | 1 | 1 | 1 | 3 | -1 | 1 | 1 | OT Lead + IT Sec: MtU #07 business case framework walkthrough. | 🟢 Low
Documentation & Evidence Standards — audit-ready output | 3 | 1 | 2 | 2 | 1 | 4 | -1 | 1 | 2 | OT Lead + IT Sec: MtU #05 and #08 — evidence standards and audit readiness. | 🟡 Medium
Stakeholder Management — bridging OT/IT/management | 2 | 2 | 0 | 2 | 0 | 3 | -1 | 1 | 1 | Ongoing — project experience is the training. Retrospective after each phase. | 🟢 Low

## 📚 Training Pathways
📚 Training Pathways ¦ Qualifications & Self-Study Routes Per Role ¦ [MtU #09]
| Qualification / Course | Description | Relevant For | Priority
CORE OT SECURITY
| GICSP — Global Industrial Cyber Security Professional | The most recognised OT security qualification. Covers ICS architecture, protocols, security assessment and incident response. Offered by GIAC/SANS. | IT Security Lead, Project Lead — highest priority | 🔴 Priority 1
| ISA/IEC 62443 Cybersecurity Certificate Program | Four-level certificate programme aligned to IEC 62443. Covers fundamentals through to expert level. Offered by ISA. | All roles — especially Project Lead and IT Security Lead | 🔴 Priority 1
| SANS ICS curriculum — ICS410, ICS515, ICS612 | Hands-on OT security training. ICS410 (essentials) is excellent for IT security professionals transitioning to OT. ICS515 covers active defence. | IT Security Lead, Project Lead | 🟠 Priority 2
| CSSA — Certified SCADA Security Architect | Vendor-neutral SCADA and ICS security architecture certification. Less common than GICSP but valued by some employers. | IT Security Lead | 🟡 Priority 3
OT / PROCESS KNOWLEDGE
| Siemens TIA Portal — introductory course | Hands-on PLC programming and configuration. Free introductory courses available on Siemens industry online support portal. | IT Security Lead, Project Lead — OT familiarisation | 🟠 Priority 2
| Rockwell Studio 5000 — introductory course | Rockwell Automation offers free eLearning for ControlLogix fundamentals. Builds OT engineer empathy for IT/security professionals. | IT Security Lead, Project Lead | 🟡 Priority 3
| SCADA/ICS simulation labs — TryHackMe, Hack The Box ICS | Hands-on OT protocol and attack simulation. Free/low cost. Excellent for IT security professionals building OT intuition. | IT Security Lead, Project Lead — self-study | 🟠 Priority 2
| Site visits and vendor training days | No substitute for spending time in a real OT environment. Request access through project relationships. Vendor open days at Siemens, Rockwell, Schneider regularly available. | IT Security Lead, Project Lead, OT Lead (cross-training) | 🟠 Priority 2
IT / NETWORK FOUNDATION — for OT engineers
| CompTIA Network+ | Solid networking fundamentals — TCP/IP, VLANs, routing, firewalls. Ideal for OT engineers who need to understand what IT Security Lead is doing. | OT Lead — network fundamentals foundation | 🟠 Priority 2
| CompTIA Security+ | Broad cybersecurity fundamentals. Covers vulnerability management, cryptography, access control, incident response. Good OT engineer entry point to security. | OT Lead transitioning toward OT security role | 🟡 Priority 3
| Networking for OT Engineers — ISA courses | ISA offers OT-specific networking courses that contextualise networking for industrial environments. More relevant than generic IT networking for OT professionals. | OT Lead | 🟡 Priority 3
COMPLIANCE & REGULATORY
| NIS2 Implementation Training | Several providers offer NIS2 compliance training for essential service operators. Covers Article 21 obligations, incident reporting, governance. | Project Lead, Plant Manager awareness | 🟠 Priority 2
| IEC 61511 — Functional Safety for SIS | Safety instrumented systems standard. Required for Safety Engineer role. Available through TÜV, Exida and ISA. | Safety Engineer — mandatory if SIL systems in scope | 🔴 Priority 1 (if SIL)
| CISM — Certified Information Security Manager | Management-level security qualification. Covers governance, risk management, incident response. Useful for Project/Compliance Lead role. | Project Lead — governance and management layer | 🟡 Priority 3

## 📖 Reference
📖 Reference ¦ The Three Tribes, RACI Principles & OT Security Career Pathways
THE THREE TRIBES
| OT Engineers | Built and maintain the systems. Understand the physical process, control logic, vendor relationships and operational constraints. Their metric is uptime. Security has historically been someone else's problem. Fear: being told their systems are insecure by someone who has never operated a PLC.
| IT Security Team | Understand vulnerability management, network architecture, firewalls, monitoring tools and compliance frameworks. Their toolkit can damage OT systems if applied without OT expertise. Assumption: IT security principles translate directly to OT. They usually don't.
| Project / Consultant | Frameworks, methodology and project management capability. Risk: becoming a translator who satisfies neither side, or driving the methodology without understanding the operational context.
RACI PRINCIPLES
| Only ONE Accountable | There must be exactly one Accountable per activity. Multiple accountable parties means no accountability. If two people are accountable, neither is.
| Responsible can be many | Multiple people can be Responsible for executing a task. But the Accountable person owns the outcome.
| Agree before the project | The RACI must be agreed and signed by all role holders before the project starts. A RACI produced after disagreements have already occurred is damage limitation, not governance.
| Review at phase gates | Review and update the RACI at each phase gate. Roles may evolve as the project progresses and team members' skills develop.
| The missing RACI risk | Without a RACI: decisions are made by whoever shouts loudest. OT engineer blocks a change nobody consulted them on. IT team breaks a control loop. Consultant produces a report that doesn't reflect operational reality.
THE BRIDGE ROLE — CAREER OPPORTUNITY
| The gap | The biggest skills gap in OT security is the gap between people who understand the process and people who understand the threat. Almost nobody understands both.
| The opportunity | IT and security professionals who develop genuine OT fluency are positioning themselves for one of the highest-demand roles in industrial cybersecurity. CRA and NIS2 are creating demand faster than the market can supply.
| The pathway | IT/security foundation + GICSP + IEC 62443 training + OT site exposure + the methodology this series documents = a genuinely differentiated profile. Not overnight — but achievable in 12–18 months with deliberate effort.
| This series | Every post in MtU is building the methodology knowledge. The templates are the deliverable set. The posts are the market presence. Combined: a portfolio that demonstrates competence without requiring 20 years of OT engineering experience.
⚡ Migrating the Unmigrateable — Study Notes ¦ [MtU #09] ¦ Template v1.0 ¦ Cite freely with attribution