## 📋 Cover
📡 ICS Operate & Monitor Programme Migrating the Unmigrateable — Study Notes ¦ [MtU #06]
Phase 5 — Operate & Monitor ¦ Continuous OT Security — Not a One-Time Exercise
PROGRAMME INFORMATION
Facility / Site Name
OT Security Owner
Organisation
Programme Start Date
Last Annual Review
Next Annual Review
| Linked MtU Templates | MtU #01 Inventory ¦ #02 Risk ¦ #03 Segmentation ¦ #04 Execution ¦ #05 Validation
| Document Version | v1.0
| Classification | CONFIDENTIAL
SHEETS IN THIS WORKBOOK
| 📡 Vulnerability Log | Monthly CVE reviews, ICS-CERT advisories, quarterly scan results.
| 🔔 Monitoring Alert Register | All OT monitoring alerts — actioned, investigated and closed.
| 🔑 Access Control Review | Quarterly review of all remote access, accounts and vendor agreements.
| 📊 OT Security Dashboard | Five key metrics tracked and trended quarterly.
| 📅 Compliance Calendar | Annual reporting cadence — monthly, quarterly and annual obligations.
| 📖 Reference | Phase 5 governance model, NIS2 reporting obligations and IEC 62443-2-1.
⚡ Migrating the Unmigrateable — Study Notes ¦ [MtU #06] ¦ Free resource — cite with attribution

## 📡 Vulnerability Log
📡 Vulnerability Management Log ¦ Phase 5 ¦ Monthly CVE Reviews & ICS-CERT Advisories ¦ [MtU #06]
📌 Sources: cve.mitre.org ¦ ICS-CERT / CISA advisories (us-cert.cisa.gov/ics) ¦ Vendor security bulletins ¦ Passive scan results
Log ID | Date Identified | Source | Asset ID(s) | CVE Reference | CVSS Score | Vulnerability Description | Affected Firmware | Patch Available? | Vendor Advisory | Risk Impact | Action Required | Owner | Target Date | Status | Date Closed | Notes
VLN-001 | 2025-04-03 | CVE database check | ICS-003 | CVE-2022-37300 | 8.1 | Remote code execution vulnerability in Schneider Sepam T40 firmware V02.06 and earlier. | V02.06 | Yes — V02.08 | Schneider Security Notification SEVD-2022-179-01 | 🟠 High — patch pending since Phase 0 | Apply firmware patch V02.08 during next maintenance window. Scheduled March 2025 — confirm completion. | OT Lead | 2025-03-31 | ✅ Patched — V02.08 applied 2025-03-28 | 2025-03-28 | Patch confirmed by OT Engineer. Firmware version verified post-patch.
VLN-002 | 2025-04-03 | CVE database check | ICS-007 | CVE-2023-31409 | 7.2 | Improper input validation in OSIsoft PI Server 2016. Potential for remote code execution via OPC-DA interface. | 3.4.390 | Yes — PI Server 2023 | OSIsoft Security Bulletin OSI-SEC-2023-001 | 🟠 High — historian bridges IT/OT | Upgrade PI Server to 2023 version. Interim: restrict OPC-DA access to approved assets only via firewall. | IT Security + OT | 2025-04-30 | ⏳ In Progress — upgrade scheduled Q2 2025 |  | Firewall interim restriction applied 2025-02-01. Full upgrade in progress.
VLN-003 | 2025-05-01 | ICS-CERT Advisory ICSA-25-119-01 | ICS-004 | CVE-2025-22891 | 9.3 | Critical authentication bypass in Siemens WinCC v7.x HMI software. Remote unauthenticated access possible. | V7.2 SP2 | No — EOL product | Siemens ProductCERT SSA-2025-119 | 🔴 Critical — EOL HMI, no patch available | Accelerate HMI replacement (already planned May 2025). Interim: physically disconnect HMI from all networks immediately. | OT Lead | IMMEDIATE | 🔴 Network disconnected 2025-05-01. HMI replacement accelerated — new unit ordered. |  | New HMI delivery confirmed 2025-05-15. Physical console operation only until replacement.
VLN-004 | 2025-05-01 | Quarterly passive scan | ICS-001-NEW | None identified | N/A | Quarterly passive scan of OT Zone 1. New PLC (S7-1500) scanned. No new CVEs. Firmware v4.1.2 confirmed current. | v4.1.2 | N/A — no CVEs | N/A | ✅ Clean | No action required. Schedule next CVE check July 2025. | OT Engineer | 2025-07-01 | ✅ Clean — no action | 2025-05-01 | Next scan due Q3 2025.
VLN-005 | 2025-05-01 | Quarterly passive scan | UNKNOWN-NEW | N/A — new device | N/A | Quarterly passive scan identified previously undocumented device on VLAN 10. IP: 192.168.10.99. Not in asset inventory. | Unknown | Unknown | Unknown | 🔴 Critical — undocumented device | Identify device immediately. Follow Phase 0 discovery process. Do not ignore — treat as critical finding until assessed. | OT Lead | IMMEDIATE | ⏳ Under investigation — physical walkdown scheduled 2025-05-03 |  | Scan finding escalated to OT Lead same day. Walkdown team assigned.
VLN-006 | 2025-07-01 | CVE database check — monthly | ICS-006 | None identified | N/A | Monthly CVE check — Honeywell Experion PKS C300 R501.2. No new CVEs published since last check. | R501.2 | N/A | N/A | ✅ Clean | No action. Next check August 2025. | OT Engineer | 2025-08-01 | ✅ Clean | 2025-07-01
VLN-007 | 2025-07-15 | Vendor security bulletin | ICS-009 | CVE-2025-31872 | 6.5 | Medium severity vulnerability in Fortinet FortiGate 7.2.x — authenticated command injection via management interface. | 7.2.5 | Yes — 7.4.2 | Fortinet PSIRT FG-IR-25-178 | ⏳ Medium — management interface only | Upgrade FortiGate firmware to 7.4.2 during next maintenance window. Restrict management interface access to admin VLAN only. | IT Security | 2025-08-31 | ⏳ Planned — upgrade scheduled August 2025 |  | Management interface already restricted to admin VLAN. Risk reduced pending patch.

## 🔔 Monitoring Alert Register
🔔 Monitoring Alert Register ¦ Phase 5 ¦ All OT Alerts Actioned & Closed ¦ [MtU #06]
Alert ID | Date / Time | Monitoring Tool | Alert Type | Severity | Asset(s) Involved | Zone | Alert Description | Initial Assessment | Root Cause | Action Taken | False Positive? | Escalated? | Owner | Date Closed | Status | Process Impact?
ALT-001 | 2025-04-08 14:23 | Nozomi Networks | New device detected | 🟠 High | Unknown — 192.168.10.99 | OT Zone 1 | Device not in asset inventory appeared on VLAN 10. MAC address not previously seen. | Potential unauthorised device or undocumented asset added without change management. | Physical walkdown identified device as replacement temperature sensor installed by maintenance contractor without formal change request. | Device added to asset inventory as ICS-011. Contractor briefed on change management requirements. PRE checklist updated to include contractor communications. | No | No | OT Lead | 2025-04-10 | ✅ Closed | No — sensor only, not connected to control loop
ALT-002 | 2025-04-15 09:47 | Nozomi Networks | Unexpected protocol detected | 🟠 High | ICS-005 (EWS) | IT/OT DMZ | EWS attempted SMB connection to ICS-001-NEW (new PLC). SMB is not an approved protocol for this conduit. | Possible lateral movement attempt or misconfigured engineering software. | IT security investigated. SMB connection was Windows automatic network discovery — not malicious. Engineering software update had changed network discovery settings. | Network discovery disabled on EWS. Firewall rule updated to explicitly deny SMB from DMZ to OT Zone 1. FW-002 updated. | Yes — benign but prompted firewall hardening | No | IT Security | 2025-04-16 | ✅ Closed | No
ALT-003 | 2025-05-01 11:15 | Nozomi Networks | CVE-2025-22891 signature match | 🔴 Critical | ICS-004 (HMI) | OT Zone 1 | Nozomi detected active exploitation attempt matching CVE-2025-22891 signature against WinCC HMI. | Active exploitation attempt against known critical vulnerability on EOL HMI. | External scan from IP 185.220.101.x attempting authentication bypass on WinCC management port. Blocked by zone firewall — no successful access. | HMI network interface physically disconnected immediately. Firewall rule FW-001 updated to deny all inbound to ICS-004. Incident reported to IT Security and management. VLN-003 accelerated. | No — confirmed active attempt | Yes — escalated to management and IT Security | OT Lead + IT Security | 2025-05-01 | ✅ Closed — HMI isolated | No — firewall blocked attempt
ALT-004 | 2025-05-15 03:22 | Nozomi Networks | Anomalous DNP3 command pattern | 🟠 High | ICS-003 (RTU) | OT Zone 2 | Unusual sequence of DNP3 direct operate commands observed outside normal operating hours. Pattern deviates from 30-day baseline. | Possible unauthorised command injection or misconfigured upstream system. | Investigation confirmed commands originated from SCADA server during automated maintenance cycle. Cycle time had been changed by vendor without updating baseline documentation. | Nozomi baseline updated. Vendor maintenance schedule documented in change log CHG-007. SCADA vendor required to notify OT team of any schedule changes in advance. | Yes — legitimate SCADA maintenance | No | OT Engineer | 2025-05-17 | ✅ Closed | No — automated maintenance only
ALT-005 | 2025-06-30 16:44 | Claroty | Firmware change detected | 🟠 High | ICS-006 (DCS) | OT Zone 3 | Claroty detected firmware version change on Honeywell DCS node. Previous: R501.1. Current: R501.2. | Unexpected firmware change — not in change management log. | Investigation: Honeywell remote diagnostic session had applied minor firmware update during vendor support call. Update not documented in change management log. | Vendor briefed — all firmware changes require formal change request and OT Lead approval regardless of whether Honeywell initiates them. CHG process updated to include vendor-initiated firmware changes. CHG-008 raised retrospectively. | No — legitimate update | No | OT Lead | 2025-07-02 | ✅ Closed | No — update was non-breaking
ALT-006 | 2025-07-10 08:31 | Nozomi Networks | Remote access outside business hours | ⏳ Medium | ICS-005 (EWS) | IT/OT DMZ | VPN session to EWS established at 08:31 on Saturday. Outside normal business hours pattern. | Possible unauthorised access or engineer working unplanned overtime. | Session confirmed as OT Engineer performing urgent firmware check following ICS-CERT advisory VLN-007. Session legitimate but not pre-notified. | Process updated: out-of-hours remote access requires prior notification to OT Lead via defined channel. Access control review checklist updated. | No — legitimate engineer | No | OT Lead | 2025-07-10 | ✅ Closed | No

## 🔑 Access Control Review
🔑 Access Control Review ¦ Phase 5 ¦ Quarterly — Remote Access, Accounts & Vendor Agreements ¦ [MtU #06]
⚠️ This review must be completed quarterly. Any access path not reviewed within 90 days should be treated as unverified and suspended pending review.
Review ID | Review Period | Access Type | User / Vendor | Asset(s) Accessed | Zone | Business Justification | MFA Enforced? | Session Logging? | Still Required? | Contract Current? | Permissions Correct? | Action Required | Owner | Review Outcome | Reviewed By | Review Date
ACR-Q2-001 | Q2 2025 (Apr–Jun) | VPN — Engineer | OT Engineer [Name] | ICS-005 (EWS) | IT/OT DMZ | Remote engineering access — approved permanent. | Yes — MFA | Yes | Yes | N/A — internal | Yes | None — access confirmed appropriate. | OT Lead | ✅ Confirmed — no change | IT Security | 2025-06-30
ACR-Q2-002 | Q2 2025 (Apr–Jun) | VPN — Vendor | Siemens Support | ICS-004 (HMI) | OT Zone 1 | Vendor support for HMI — contract active until 2025-12-31. | Yes — MFA | Yes | Yes — until HMI replaced | Yes — expires 2025-12-31 | Yes — read + remote desktop only | REVOKE access after HMI replacement (planned May 2025). Do not extend contract. | OT Lead | ⚠️ Flag — revoke post HMI migration | OT Lead | 2025-06-30
ACR-Q2-003 | Q2 2025 (Apr–Jun) | RDP — Vendor | Schneider Electric | ICS-003 (RTU) | OT Zone 2 | Patch support access — required for CVE-2022-37300 patch. | Yes — MFA | Yes | No — patch applied 2025-03-28 | No — work order closed | N/A — work complete | REVOKE immediately — patch complete, no ongoing justification. | IT Security | 🔴 Revoked 2025-06-30 | IT Security | 2025-06-30
ACR-Q2-004 | Q2 2025 (Apr–Jun) | Jump Server — Internal | IT Security Team | All zones — monitoring only | All | OT monitoring and incident response — permanent requirement. | Yes — MFA | Yes | Yes | N/A — internal | Yes — read-only monitoring | None — access confirmed appropriate. | IT Security | ✅ Confirmed — no change | IT Security | 2025-06-30
ACR-Q2-005 | Q2 2025 (Apr–Jun) | VPN — Vendor | OSIsoft / AVEVA | ICS-007 (Historian) | IT/OT DMZ | Historian maintenance — contract expires 2026-06-30. | Yes — MFA | Yes | Yes | Yes — expires 2026-06-30 | Yes — historian admin only | Diarise contract review for 2026-05-01. Confirm access revocation process with vendor. | OT Lead | ✅ Confirmed — diarise 2026-05-01 | OT Lead | 2025-06-30
ACR-Q2-006 | Q2 2025 (Apr–Jun) | Legacy account — inactive | Former OT Engineer [Name] | ICS-005 (EWS) | IT/OT DMZ | Former employee — left organisation 2025-02-28. Account not disabled. | N/A — account inactive | Yes | No — employee left | N/A | No — employee no longer employed | DISABLE IMMEDIATELY. Review all session logs for this account since 2025-02-28. | IT Security | 🔴 Disabled 2025-06-30. Logs reviewed — no unauthorised sessions. | IT Security | 2025-06-30
ACR-Q3-001 | Q3 2025 (Jul–Sep) | VPN — Engineer | OT Engineer [Name] | ICS-005 (EWS) | IT/OT DMZ | Remote engineering access — approved permanent. | Yes — MFA | Yes | Yes | N/A — internal | Yes | None — access confirmed appropriate. | OT Lead | ✅ Confirmed — no change | IT Security | 2025-09-30
ACR-Q3-002 | Q3 2025 (Jul–Sep) | VPN — Vendor | Siemens Support | ICS-004-NEW (new HMI) | OT Zone 1 | Vendor support for new HMI — contract confirmed post-migration. | Yes — MFA | Yes | Yes | Yes — new contract 2025-2028 | Yes — confirmed with new HMI vendor terms | None — access confirmed appropriate for new device. | OT Lead | ✅ Confirmed — no change | OT Lead | 2025-09-30

## 📊 OT Security Dashboard
📊 OT Security Dashboard ¦ Phase 5 ¦ Five Key Metrics — Tracked & Trended Quarterly ¦ [MtU #06]
Track these five metrics quarterly. Trend direction matters more than any single number.
| Metric | Q1 2025 | Q2 2025 | Q3 2025 | Q4 2025 | Trend
% Assets with Active Vendor Support
Mean Time to Patch Known CVEs (days)
% Remote Access Paths with MFA
OT Monitoring Alerts — Open at Quarter End
% Assets with Validated Compensating Controls (EOL devices)
| Target: 100% of EOL assets have documented controls. No unmanaged EOL devices. |  | 67% | 100% | 100% | ⏳ Pending

## 📅 Compliance Calendar
📅 OT Security Compliance Calendar ¦ Phase 5 ¦ Monthly, Quarterly & Annual Obligations ¦ [MtU #06]
Activity ID | Cadence | Activity | Output / Deliverable | Standard / Obligation | Owner | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
CAL-001 | Monthly | CVE database check — all assets in inventory | Vulnerability log entries per asset | NIS2 Art. 21 / IEC 62443 | OT Engineer | ✅ | ✅ | ✅ | ✅ | ✅ | ✅ | ✅
CAL-002 | Monthly | ICS-CERT / CISA advisory review | Advisory log. Actions for applicable advisories | NIS2 Art. 21 | IT Security | ✅ | ✅ | ✅ | ✅ | ✅ | ✅ | ✅
CAL-003 | Monthly | OT monitoring alert review — open items | Alert register update. All items actioned or justified | NIS2 Art. 21(2)(f) | IT Security + OT | ✅ | ✅ | ✅ | ✅ | ✅ | ✅ | ✅
CAL-004 | Monthly | Vulnerability log status update | Updated status on all open VLN items | Internal programme | OT Lead | ✅ | ✅ | ✅ | ✅ | ✅ | ✅ | ✅
CAL-005 | Quarterly | Access control review — all remote access paths | Completed ACR sheet. Actions raised and closed | NIS2 Art. 21(2)(i) | Owner: IT Security + OT; Mar: ✅; Jun: ✅; Sep: ✅; Dec: ✅
CAL-006 | Quarterly | Passive network scan — compare vs asset inventory | Scan report. New devices investigated. Inventory updated | IEC 62443-2-1 | Owner: OT Engineer; Mar: ✅; Jun: ✅; Sep: ✅; Dec: ✅
CAL-007 | Quarterly | Risk register review — update scores, new items | Updated risk register. New priority shortlist items | NIS2 Art. 21(2)(a) | Owner: OT Lead; Mar: ✅; Jun: ✅; Sep: ✅; Dec: ✅
CAL-008 | Quarterly | OT security dashboard update — five metrics | Updated dashboard. Trend commentary | Internal programme | Owner: OT Lead; Mar: ✅; Jun: ✅; Sep: ✅; Dec: ✅
CAL-009 | Quarterly | OT security review meeting — management report | Meeting minutes. Actions. Management report | NIS2 Art. 21 | Owner: OT Lead + Management; Mar: ✅; Jun: ✅; Sep: ✅; Dec: ✅
CAL-010 | Annual | Full vulnerability assessment — all assets, all layers | Annual assessment report. Updated risk register | NIS2 Art. 21 / IEC 62443 | Owner: OT Lead + IT Security; Dec: ✅
CAL-011 | Annual | Asset inventory reconciliation — passive scan vs documented | Reconciliation report. Discrepancies investigated | NIS2 Art. 21(2)(h) | Owner: OT Engineer; Dec: ✅
CAL-012 | Annual | Compliance evidence pack refresh | Updated MtU #01–#06 evidence for current year | NIS2 Art. 21 / Cyber insurance | Owner: OT Lead; Dec: ✅
CAL-013 | Annual | OT security policy and procedure review | Updated policies. Sign-off by management | IEC 62443-2-1 | Owner: OT Lead + Management; Dec: ✅
CAL-014 | Annual | Lessons learned — annual programme review | Annual lessons learned document | Internal programme | Owner: OT Lead; Dec: ✅
CAL-015 | Annual | Cyber insurance evidence submission | Insurance renewal evidence pack | Cyber insurance requirement | Owner: OT Lead + Finance; Dec: ✅

## 📖 Reference
📖 Reference ¦ Phase 5 Governance, NIS2 Reporting & IEC 62443-2-1
PHASE 5 — FIVE PILLARS
| ① Asset Management | Living asset inventory — updated on every change. Integrated into change management process. Annual full reconciliation. Named owner.
| ② Vulnerability Management | Monthly CVE checks. Quarterly passive scans. Annual full assessment. Ad hoc response to ICS-CERT critical advisories. Results feed back to Phase 1 risk register.
| ③ Continuous Monitoring | OT monitoring tool (Nozomi/Claroty/Dragos) providing asset discovery, behavioural baselining and threat detection. Alerting — not just logging. Defined incident response process for OT.
| ④ Access Control Review | Quarterly review of all remote access, accounts and vendor agreements. Any path not reviewed within 90 days treated as unverified and suspended. Former employee accounts disabled on departure.
| ⑤ Compliance Reporting | Monthly vulnerability log. Quarterly dashboard and management report. Annual compliance evidence pack refresh. NIS2 incident reporting within 24h (early warning) and 72h (full notification).
NIS2 — INCIDENT REPORTING OBLIGATIONS
| Early Warning — 24 hours | Initial notification to national competent authority within 24 hours of becoming aware of a significant incident. Includes whether the incident is suspected to be caused by unlawful or malicious act.
| Incident Notification — 72 hours | Full notification within 72 hours including: initial assessment of incident, severity and impact, indicators of compromise where available.
| Intermediate Report | Upon request from competent authority — status update on incident and response measures.
| Final Report — 1 month | Detailed description of incident, type of threat or root cause, mitigation measures applied, cross-border impact if any.
| Significant incident definition | An incident with significant impact on service provision — substantial disruption, financial loss, or affecting other organisations. OT incidents at essential service operators typically qualify.
IEC 62443-2-1 — MANAGEMENT SYSTEM REQUIREMENTS
| Security Policy | Documented OT security policy signed by senior management. Scope, objectives, roles and responsibilities defined.
| Risk Assessment Process | Repeatable, documented process for identifying and assessing OT security risks. Linked to asset inventory and threat intelligence.
| Competency & Training | Defined competency requirements for OT security roles. Training records maintained. Awareness programme for all OT personnel.
| Supplier Management | Process for assessing and managing OT security risks from suppliers and vendors. Includes remote access agreements and contract terms.
| Continuous Improvement | Process for reviewing and improving the OT security management system. Includes lessons learned, audit findings and incident review.
GOVERNANCE — WHO OWNS OT SECURITY?
| The ambiguity risk | In most organisations, IT says OT is outside their scope. OT engineers say security is IT's job. The CISO says they don't have visibility into OT. This ambiguity is itself a critical risk finding and the first thing a competent authority will ask about.
| OT Security Owner | A named individual accountable for the programme. Not 'the OT team.' One person. With authority and a reporting line to senior management.
| Escalation path | Defined: what decisions go to plant management, what go to the board, what go to the CISO. Documented and tested — not assumed.
| OT Security Review Meeting | At least quarterly. Attended by OT Lead, IT Security, plant management. Minutes and actions recorded. OT risk on the same register as business risk.
⚡ Migrating the Unmigrateable — Study Notes ¦ [MtU #06] ¦ Template v1.0 ¦ Cite freely with attribution