## 📄 Executive Summary
💼 OT Security Migration — Business Case Migrating the Unmigrateable — Study Notes ¦ [MtU #07]
Executive Summary ¦ For Board / Senior Management Review
FACILITY & PROGRAMME INFORMATION
Facility / Site
Prepared By
Date
| Programme Scope | Legacy ICS migration — Phases 0–5
| Total Devices in Scope | 11 ICS assets — 3 Critical, 4 High, 4 Medium/Low priority
| Programme Duration | 24 months — phased investment
THE COST OF DOING NOTHING
| Estimated cost per hour of unplanned OT downtime | 45000
| Estimated duration of ransomware/major OT incident (weeks) | 3
| ⚠️ Total estimated financial exposure — major OT incident | 32680000
| Maximum NIS2 penalty — essential entity | 10000000
| Management personal liability exposure | Quantify with insurer / legal
| Cyber insurance — uninsured exposure if controls not demonstrated | Quantify with insurer / legal
PROPOSED PROGRAMME — PHASED INVESTMENT
| Phase | Scope | Investment | Risk Retired | Cumulative Risk Reduction
| Phase 0+1 Discover & Assess | Asset inventory + risk scoring. Know what you have. | 25000 | Eliminates unknown risk exposure. Baseline for all subsequent decisions. | Foundation — all subsequent phases depend on this
| Phase 2 Segment & Isolate | Network segmentation, remote access hardening, compensating controls. | 85000 | Eliminates undocumented access paths. Reduces exposure of EOL devices pending replacement. NIS2 Art.21(2)(e) met. | 🟠 High risks reduced to 🟡 Medium with controls in place
| Phase 3a Critical Migrations | Replace 3 Critical-priority devices (ICS-001, ICS-004, ICS-010 decommission). | 180000 | Removes 3 uninsurable assets. Eliminates CVE-2021-37185 and CVE-2019-13945 exposure. | 🔴 Critical assets → ✅ Validated & compliant
| Phase 3b High Migrations | Replace/patch remaining High-priority assets (ICS-003, ICS-007). | 95000 | Full CVE remediation. Historian upgraded — IT/OT bridge risk eliminated. | 🟠 High assets → ✅ Validated & compliant
| Phase 4+5 Validate & Operate | Validation evidence pack + ongoing monitoring programme. | 35000 | Audit-ready compliance evidence. NIS2 Article 21 fully demonstrable. Insurance position improved. | Full programme — defensible compliance posture
| TOTAL PROGRAMME INVESTMENT |  | 420000 | Full NIS2 Article 21 compliance demonstrable
RECOMMENDATION & DECISION REQUIRED
| Approve Phase 0+1 immediately | Low investment (€25,000). Establishes the evidence base for all subsequent decisions. Cannot properly scope later phases without this.
| Approve Phase 2 in Q2 2025 | Segmentation (€85,000) delivers the fastest risk reduction per euro spent. Also addresses NIS2 Art.21(2)(e) immediately.
| Approve Phases 3a–5 as programme | Remaining €310,000 spread across 18 months. Each phase independently auditable. Board review after Phase 2 before Phase 3 approval.
⚡ Migrating the Unmigrateable — Study Notes ¦ [MtU #07] ¦ Full workbook: see sheets below

## 💥 Incident Cost Model
💥 OT Incident Cost Model ¦ The Cost of Doing Nothing ¦ [MtU #07]
Populate the yellow cells with facility-specific figures. All calculations update automatically.
PRODUCTION LOSS MODEL
| Hourly production output (units/hr) | 1000
| Product value per unit (€) | 45
Hourly revenue (auto-calculated)
| Gross margin % | 35
Hourly margin at risk (auto-calculated)
| Fixed costs per hour (labour, utilities, etc.) | 8500
Total hourly downtime cost (auto-calculated)
INCIDENT SCENARIO MODELLING
| Scenario | Duration | Estimated Cost | Probability (annual) | Risk-Adjusted Cost
| Targeted ransomware — OT network | 3 weeks (504 hrs) | 15% | 0.15
| Accidental misconfiguration — process fault | 8 hrs | 35% | 0.35
| Legacy CVE exploited — single device | 48 hrs | 20% | 0.2
| Undocumented remote access — breach | 2 weeks (336 hrs) | 10% | 0.1
| Supply chain compromise — vendor access | 1 week (168 hrs) | 8% | 0.08
TOTAL ANNUALISED RISK EXPOSURE (pre-programme)
REGULATORY & INSURANCE EXPOSURE
| NIS2 maximum penalty — essential entity | 10000000
| NIS2 — management personal liability | Unlimited — personal criminal liability possible
| Estimated current cyber insurance premium (annual) | 45000
| Estimated post-programme premium reduction | 15–25% reduction — confirm with insurer
| Uninsured exposure if controls not demonstrated | Confirm with insurer — potential full claim rejection

## 📈 Phased Investment Plan
📈 Phased Investment Plan ¦ Risk Reduction Per Euro Spent ¦ [MtU #07]
Phase | Activities | Key Deliverables | Investment (€) | Timeline | Risk Items Retired | Risks Remaining | NIS2 Obligations Met | Go/No-Go Criteria | Board Approval Required | Status
Phase 0+1 Discover & Assess | Asset inventory (Phase 0). Risk scoring matrix (Phase 1). Zone map. Priority shortlist. | MtU #01 inventory. MtU #02 risk matrix. Priority shortlist. | 25000 | Month 1–2 | Complete picture of OT risk landscape. No more unknown unknowns. | All identified risks still present — but now documented and prioritised. | Art.21(2)(a) — risk analysis baseline established. | All assets discovered and risk-scored. Priority shortlist agreed with plant management. | Yes — programme approval gate | ⏳ Planned
Phase 2 Segment & Isolate | VLAN segmentation. OT firewall deployment. Remote access hardening. Compensating controls for EOL devices. | MtU #03 segmentation design. Firewall rule register. Remote access register. Change log. | 85000 | Month 3–6 | Undocumented access paths eliminated. EOL devices isolated with documented controls. NIS2 Art.21(2)(e) met. | EOL devices still present — but now behind compensating controls with committed replacement dates. | Art.21(2)(e) — network segmentation. Art.21(2)(i) — remote access controls. | All zones segmented. 100% remote access paths documented and MFA'd. Compensating controls signed off. | No — within programme approval | ⏳ Planned
Phase 3a Critical Migrations | Replace ICS-001 (EOL PLC). Replace ICS-004 (EOL HMI). Decommission ICS-010 (undocumented modem). | MtU #04 execution records per device. MtU #05 validation reports. Updated asset inventory. | 180000 | Month 7–12 | 3 Critical-priority assets remediated. CVE-2019-13945 and CVE-2021-37185 eliminated. 2 EOL devices → Active support. | 4 High-priority assets still pending Phase 3b. All have compensating controls from Phase 2. | Art.21(2)(e)(f)(h) — controls validated, asset management updated. | All 3 critical devices migrated and validated. Validation reports signed. Risk register updated. | Yes — Phase 3a approval gate | ⏳ Planned
Phase 3b High Migrations | Patch ICS-003 (RTU — CVE-2022-37300). Upgrade ICS-007 (Historian — CVE-2023-31409 + OPC-UA migration). | MtU #04 execution records. MtU #05 validation reports. Updated network topology. | 95000 | Month 13–18 | All known CVEs remediated. Historian upgraded — IT/OT bridge risk eliminated. OPC-UA replaces OPC-DA. | Ongoing monitoring and quarterly reviews required. No critical or high unmitigated risks remaining. | Art.21(2)(e)(f)(h)(i) — full controls validated. | All CVEs patched or devices replaced. Validation signed. No open critical or high risk items. | No — within programme approval | ⏳ Planned
Phase 4+5 Validate & Operate | Compliance evidence pack. Audit readiness checklist. Ongoing vulnerability management. Quarterly reviews. | MtU #05 evidence pack. MtU #06 operate & monitor programme. Annual compliance calendar. | 35000 | Month 18–24 ongoing | Full NIS2 Article 21 compliance demonstrable. Audit-ready evidence pack. Insurance position improved. | Ongoing monitoring required — Phase 5 has no end date. Annual evidence pack refresh. | Full NIS2 Article 21 compliance. IEC 62443 SL-2 demonstrated. | Annual compliance evidence pack complete. OT security owner named. Quarterly review cadence established. | No — operational | ⏳ Planned
TOTAL PROGRAMME INVESTMENT |  |  | 420000 |  | All Critical and High risks retired. Full NIS2 Article 21 compliance demonstrable.

## 📉 Risk Reduction Tracker
📉 Risk Reduction Tracker ¦ Asset-Level Risk Journey ¦ [MtU #07]
Asset ID | Asset Name | Pre-Programme Risk | Risk Score (Phase 1) | After Phase 2 | After Phase 3a | After Phase 3b | After Phase 4+5 | Investment Phase | Est. Cost | Current Status
ICS-001 | PLC-UNIT-01 | 🔴 Critical | 36 | 🟠 High (controls) | ✅ Migrated | ✅ Validated | ✅ Closed | Phase 3a | 55000 | ⏳ Phase 3a planned
ICS-002 | PLC-UNIT-02 | 🟢 Low | 2 | 🟢 Low | 🟢 Low | 🟢 Low | 🟢 Low | None — monitor | 0 | ✅ No action needed
ICS-003 | RTU-REMOTE-01 | 🟠 High | 60 | 🟡 Medium (modem removed) | 🟡 Medium | ✅ Patched | ✅ Closed | Phase 3b | 35000 | ⏳ Phase 3b planned
ICS-004 | HMI-CTRL-01 | 🔴 Critical | 45 | 🟠 High (isolated) | ✅ Migrated | ✅ Validated | ✅ Closed | Phase 3a | 75000 | ⏳ Phase 3a planned
ICS-005 | EWS-ENG-01 | 🟡 Medium | 24 | ✅ Hardened (MFA) | ✅ Hardened | ✅ Hardened | ✅ Closed | Phase 2 | 8000 | ✅ Phase 2 complete
ICS-006 | DCS-NODE-01 | 🟡 Medium | 20 | 🟡 Medium (data diode) | 🟡 Medium | 🟡 Medium | ✅ Closed | Phase 4+5 | 0 | ✅ Monitoring only
ICS-007 | HIST-01 | 🟠 High | 24 | 🟡 Medium (FW rules) | 🟡 Medium | ✅ Upgraded | ✅ Closed | Phase 3b | 60000 | ⏳ Phase 3b planned
ICS-008 | SENSOR-TMP-01 | 🟢 Low | 3 | 🟢 Low | 🟢 Low | 🟢 Low | 🟢 Low | None — monitor | 0 | ✅ No action needed
ICS-009 | FIREWALL-OT-01 | 🟡 Medium | 15 | ✅ Audited (Phase 2) | ✅ Audited | ✅ Audited | ✅ Closed | Phase 2 | 5000 | ✅ Phase 2 complete
ICS-010 | MODEM-4G-UNKN | 🔴 Critical | 125 | ✅ Disconnected | ✅ Decommissioned | ✅ Decommissioned | ✅ Closed | Phase 2 | 2000 | ✅ Disconnected — Phase 0

## 🎯 Sensitivity Analysis
🎯 Sensitivity Analysis ¦ What If Costs Are Higher? What If an Incident Occurs? ¦ [MtU #07]
Finance will ask: what if it costs more than estimated? What if an incident occurs during the programme? This sheet answers both.
SCENARIO 1 — COST OVERRUN
| Scenario | Base Case | +25% Overrun | +50% Overrun | Still cheaper than...
| Total programme investment | 420000 | 525000 | 630000 | One week of ransomware downtime
| Phase 0+1 only | 25000 | 31250 | 37500 | One shift of unplanned downtime
| Phase 2 only | 85000 | 106250 | 127500 | Two days of unplanned downtime
| Phase 3a — critical migrations | 180000 | 225000 | 270000 | Four days of unplanned downtime
SCENARIO 2 — INCIDENT OCCURS DURING PROGRAMME
If an incident occurs after Phase 2 is complete, the financial and regulatory position is significantly better than pre-programme. This table shows why.
| Factor | Pre-Programme | After Phase 2 | After Phase 3 Complete
| Blast radius of incident | Entire flat network — all assets reachable | Contained to compromised zone only | Single device — compensating controls limit spread
| Undocumented access paths | Multiple unknown — 4G modem, legacy modem | All documented and controlled | None — all paths verified
| NIS2 penalty exposure | Full exposure — no demonstrable controls | Reduced — segmentation evidence available | Minimal — full Article 21 compliance demonstrable
| Insurance claim position | Uncertain — controls not demonstrable | Stronger — Phase 2 evidence available | Strong — full validation evidence pack
| Recovery time estimate | Weeks — no baseline, no documentation | Days — baseline and change records exist | Hours to days — full documentation and staging environment
| Management liability | High — no documented programme | Reduced — programme in progress | Low — full documented programme with evidence

## 📖 Reference
📖 Reference ¦ Business Case Language, OT Translation Guide & Financial Framework
TRANSLATING OT TO BUSINESS LANGUAGE
| EOL device with CVE | Uninsurable asset with a known, publicly documented exploit path.
| No network segmentation | Single point of failure across the entire facility — one compromised device reaches everything.
| Legacy protocol with no auth | An open door with no lock. Visible from any connected network. No credentials required to send commands.
| 99.9% uptime requirement | €X per hour revenue at risk during any unplanned incident. Calculate using the Incident Cost Model sheet.
| NIS2 Article 21 compliance | Legal obligation. Management personal liability established by statute. Not a best practice — a legal requirement already in force.
| Compensating controls | Interim risk mitigation — not a permanent solution. Time-bounded with committed replacement dates.
| Phase 0 asset discovery | You cannot protect what you don't know you have. The inventory is the prerequisite for every other investment.
| Validation evidence pack | The documentation that answers an auditor, insurer or board when they ask: how do you know your controls work?
THE FOUR NUMBERS EVERY BUSINESS CASE NEEDS
| ① Hourly downtime cost | Lost margin + fixed costs per hour. For most industrial facilities: €10,000–€100,000/hr. Calculate in the Incident Cost Model sheet.
| ② Regulatory exposure | NIS2: up to €10M or 2% of global annual turnover. Management personal liability. ICS-CERT incidents triggering mandatory reporting within 24 hours.
| ③ Insurance position | Current premium vs. post-programme premium. Uninsured exposure if controls cannot be demonstrated. Confirm with your insurer.
| ④ Cost of doing nothing | Annualised risk exposure from the scenario model. This is the number that reframes the investment conversation. The programme cost is not a spend — it's the price of avoiding a much larger unplanned spend.
PHASED APPROVAL STRATEGY
| Why phased approval works | A €420K programme presented as one line item gets deferred. The same programme presented as five phases with discrete risk reduction at each stage gets approved incrementally.
| Phase 0+1 as the entry point | €25K to know what you have. Impossible to argue against. Creates the evidence base that justifies every subsequent phase. Always the right first ask.
| Board gates | Phase 0+1 and Phase 3a require board approval gates. Phases 2, 3b and 4+5 proceed within programme approval. This limits the number of return visits while maintaining governance.
| The no-decision is a decision | Deferring the programme is not a neutral act. It is an active choice to accept the annualised risk exposure calculated in the scenario model. Make that explicit in the business case.
⚡ Migrating the Unmigrateable — Study Notes ¦ [MtU #07] ¦ Template v1.0 ¦ Cite freely with attribution